## IS-23D-0-UNI001-26-15
Schedule for project : Supply and install camera check carton line 2 system at ORAL Cu Chi
Duration : 3 Weeks ( W1-W3)
| Code Project : | IS-23D-0-UNI001-26-15
| Name Project : | Supply and install camera check carton line 2 system at ORAL Cu Chi
| Update date : | 2023-11-16
| P.I.C : | Trung Dũng
No. | Content |  | P.I.C | Status | Note | Plan |  | Actual |  | Duration (days) | T/A
[12 empty] | W1 | [6 empty] | W2 | [6 empty] | W3 | [6 empty] | W4
[6 empty] | Start Date | End Date | Start Date | End Date |  |  | 2023-11-20 | 2023-11-21 | 2023-11-22 | 2023-11-23 | 2023-11-24 | 2023-11-25 | 2023-11-26 | 2023-11-27 | 2023-11-28 | 2023-11-29 | 2023-11-30 | 2023-12-01 | 2023-12-02 | 2023-12-03 | 2023-12-04 | 2023-12-05 | 2023-12-06 | 2023-12-07 | 2023-12-08 | 2023-12-09 | 2023-12-10 | 2023-12-11 | 2023-12-12 | 2023-12-13 | 2023-12-14 | 2023-12-15 | 2023-12-16 | 2023-12-17 | 2023-11-16 | 2023-11-17 | 2023-11-18 | 2023-11-19 | 2023-11-20 | 2023-11-21 | 2023-10-03 | 2023-10-04 | 2023-10-05 | 2023-10-06 | 2023-10-07 | 2023-10-08
[12 empty] | 1900-01-19 | 1900-01-20 | 1900-01-21 | 1900-01-22 | 1900-01-23 | 1900-01-24 | 1900-01-25 | 1900-01-26 | 1900-01-27 | 1900-01-28 | 1900-01-29 | 1900-01-31 | 1900-02-01 | 1900-02-02 | 1900-02-03 | 1900-02-04 | 1900-02-05 | 1900-02-06 | 1900-02-07 | 1900-02-08 | 1900-02-09 | 1900-02-10 | 1900-02-11 | 1900-02-12 | 1900-02-13 | 1900-02-14 | 1900-02-15 | 1900-02-16 | 1900-02-15 | 1900-02-16 | 1900-02-17 | 1900-02-18 | 1900-02-19 | 1900-02-20 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1900-01-07
[12 empty] | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Thu | Fri | Sat | Sun | Mon | Tue | Tue | Wed | Thu | Fri | Sat | Sun
I | Thiết kế giao diện |  |  |  |  | 2023-11-20 | 2023-11-22 |  |  | 3 | bar: Mon to Wed
1 | Giao diện màn hình Home |  |  |  |  | 2023-11-20 | 2023-11-20 |  |  | 1 | bar: Mon
2 | Giao diện màn hình Master Data |  |  |  |  | 2023-11-20 | 2023-11-21 |  |  | 1 | bar: Mon
3 | Giao diện màn hình Report |  |  |  |  | 2023-11-21 | 2023-11-22 |  |  | 1 | bar: Tue
4 | Giao diện màn hình Setting - About |  |  |  |  | 2023-11-22 | 2023-11-22 |  |  | 1 | bar: Wed
II | Xử lý |  |  |  |  | 2023-11-23 | 2023-11-30 |  |  | 7 | bar: Thu to Fri
1 | Giao diện màn hình Home |  |  |  |  | 2023-11-23 | 2023-11-24 |  |  | 2 | bar: Thu to Fri
2 | Giao diện màn hình Master Data |  |  |  |  | 2023-11-27 | 2023-11-28 |  |  | 2 | bar: Mon to Tue
3 | Giao diện màn hình Report |  |  |  |  | 2023-11-29 | 2023-11-30 |  |  | 2 | bar: Wed to Thu
4 | Giao diện màn hình Setting - About |  |  |  |  | 2023-11-30 | 2023-12-01 |  |  | 2 | bar: Thu to Fri
III | Deploy - Theo dõi |  |  |  |  | 2023-12-04 | 2023-12-08 |  |  | 5 | bar: Mon to Fri
1 | Deploy |  |  |  |  | 2023-12-04 | 2023-12-04 |  |  | 1 | bar: Mon
2 | Theo Dõi |  |  |  |  | 2023-12-04 | 2023-12-08 |  |  | 5 | bar: Mon to Fri